Project Proposal

YEDI + TIDAL

Two-Sided Staffing Platform

From Admin Panel to Production Product

Version: v1.0

Authored by: Chris Vu

Approved by: Bryan Du

Hanoi, July 6th 2026

Presenter

| Presenter | Position | Division |
| --- | --- | --- |
| Bryan Du | Solutions / Delivery | Global Delivery |

Edit History

| Date | Version | Description | Editor |
| --- | --- | --- | --- |
| Jul 6, 2026 | 1.0 | Create | Chris Vu |

Approval

| Approved date | Version | Approved by | Position |
| --- | --- | --- | --- |
|  | 1.0 | Bryan Du | CDO |

Table of Contents

1. Project Overview	5

Current State — Directly Verified	5

Solution Value Proposition	5

Project Objectives	6

2. Project Scope	6

2.1 In-Scope Items	6

Phase 1	6

2.1.1 Identity, Authentication & Access	6

2.1.2 Brand/School Portal	6

2.1.3 Candidate/Teacher Portal	6

2.1.4 Adverts & Job Lifecycle	7

2.1.5 Applications, Matching & Booking (Core Loop)	7

2.1.6 Compliance & Right-to-Work	7

2.1.7 Timesheets & Attendance	7

2.1.8 Billing (Invoice / Payslip)	7

2.1.9 Notifications & Communications	7

2.1.10 Multi-Tenancy & Non-Functional	7

Phase 2	7

2.1.11 Phase 2 — Automation, Full Yedi & Polish	7

2.2 Out-of-Scope Items	7

2.3 Dependencies and Assumptions	8

3. Solution Approach	8

3.1 Delivery Methodology	9

3.2 Communication & Collaboration	9

3.3 Quality Assurance Strategy	9

4. Technical Requirements	9

4.1 Core Architectural Principles	10

4.2 System Architecture	10

4.3 Architecture Options — Shared vs Separate	10

4.4 Technical Configuration	10

5. Master Schedule	11

5.1 Master Schedule Overview	11

5.2 Phase 1 (MVP) Sprint Breakdown	11

5.3 Phase 2 (Enhancement) Sprint Breakdown	12

6. Quotation & Work Breakdown Structure	12

6.1 Work Breakdown Structure	12

6.2 Team Structure & Cost Breakdown	13

6.3 Payment Milestones	14

7. Future Enhancements Roadmap	15

# 1. Project Overview

Yedi and Tidal are a two-sided staffing platform — Yedi connects schools with teachers; Tidal connects brands with candidates — built on a Laravel + Filament admin panel. Sotatek proposes a “keep & extend” programme (no rebuild) that turns the internal admin panel into a production, self-service, transacting product, delivered on a single shared multi-tenant foundation.

Figures in this proposal are indicative — based on a hands-on assessment of the live admin systems without source-code access. Sprint 1 of Phase 1 includes a source-code audit that confirms or fine-tunes these figures before Sprint 2 begins; there is no separate pre-project phase or additional approval gate.

## Current State — Directly Verified

We logged in and tested the live admin of both platforms (Tidal on 2026-06-29; Yedi + Tidal re-verification on 2026-07-03). The backbone is real and reusable — roughly a quarter of a full platform already exists:

- Rich data model: Adverts (rate, charge %, shift, address, docs), Candidates (4-tab profile, references, compliance status, ID/video/contract storage), Brands/Schools, and System settings.

- Working admin CRUD: full resource coverage, status filters, bulk actions and financial dashboard widgets.

- Partial application logic: creating an Application correctly updates the related records (accepted-application, counters).

- Per-tenant configuration: Yedi carries 5 education job-roles (QTS) plus a “DBS Evidence” catalogue; Tidal carries its charge defaults.

- Key finding: Yedi and Tidal are currently the SAME codebase — separately deployed, re-labelled (School/Teacher/Job vs Brand/Candidate/Advert) and configured per tenant.

- Assessment: across ~110 features assessed: ~23 done, ~41 partial, ~46 missing.

## Solution Value Proposition

What remains is the transaction engine and the self-service surfaces that turn the admin panel into a sellable product. Because every missing engine is identical for both platforms, we build it once on a multi-tenant foundation:

- Two self-service portals (Brand/School + Candidate/Teacher).

- Core booking engine: Application → Matching → Offer/Accept → Booking.

- Billing engine: invoice/payslip generation + PDF + lifecycle.

- Compliance & right-to-work engine with enforcement.

- Timesheets, multi-party authentication, RBAC and notifications.

- Shared multi-tenant white-label foundation — ~40–45% cheaper than two separate builds.

## Project Objectives

- Turn the internal admin panel into a production, self-service, transacting two-sided platform.

- Launch the Tidal MVP in ~3 months — including the Sprint 1 source-code audit — on a shared multi-tenant foundation.

- Enable Yedi in Phase 2 — including its UI/UX, tenant configuration and the education compliance layer (DBS/safeguarding — a mandatory gate).

- Deliver production-grade security, a GDPR baseline, automated tests and CI/CD.

# 2. Project Scope

## 2.1 In-Scope Items

Delivery is organised into two Phases. Phase 1 delivers a launchable Tidal MVP on a shared multi-tenant foundation, built so that additional industry verticals (incl. Yedi) can be switched on via configuration in a later phase. Phase 2 fully enables Yedi — UI/UX, tenant configuration, and the education compliance layer (DBS/safeguarding) — alongside payment automation, full education matching and reporting depth.

A note on pricing precision: the effort and cost figures in this proposal are indicative — built from a hands-on but black-box assessment of the live systems (no source-code access yet). Sprint 1 of Phase 1 includes a source-code audit alongside environment setup and foundation work; by the end of Sprint 1 we confirm these figures against the real codebase and flag any material change before Sprint 2 begins. This confirmation happens inside Phase 1 — it is not a separate phase, and its cost and timeline are already included in the ~3-month.

## Phase 1

Phase 1 includes the full Tidal platform (UI/UX, Matching Engine, full features) and the shared multi-tenant foundation. Yedi — including its UI/UX, tenant configuration and education compliance layer (DBS/safeguarding) — is built entirely in Phase 2.

### 2.1.1 Identity, Authentication & Access

- Multi-party authentication (Brand/School, Candidate/Teacher, Admin) with password reset and 2FA.

- Role-based access control (RBAC) across portals and admin.

### 2.1.2 Brand/School Portal

- Post and manage staffing requests / adverts; review applicants.

- Booking management and invoice view.

### 2.1.3 Candidate/Teacher Portal

- Onboarding, profile, upload evidence, set availability.

- Search, apply, accept; timesheet submission and payslip view.

### 2.1.4 Adverts & Job Lifecycle

- Advert creation, status lifecycle, and publishing to the candidate portal.

### 2.1.5 Applications, Matching & Booking (Core Loop)

- Application → Matching → Offer/Accept → Booking, with allocation and auto-status.

- Availability model + basic clash detection.

### 2.1.6 Compliance & Right-to-Work

- Compliance engine with rules, enforcement and evidence capture (right-to-work gate).

### 2.1.7 Timesheets & Attendance

- Shift → hours → pay-basis capture feeding billing and payslips.

### 2.1.8 Billing (Invoice / Payslip)

- Invoice and payslip generation + PDF output + lifecycle (using existing bank/terms/template config).

### 2.1.9 Notifications & Communications

- Basic notifications: email-first plus key SMS (booking / timesheet / compliance).

### 2.1.10 Multi-Tenancy & Non-Functional

- Shared multi-tenant white-label foundation, architected to support additional industry verticals — Yedi is enabled via configuration in Phase 2.

- Security + GDPR baseline, automated tests and CI/CD; Tidal go-live.

## Phase 2

### 2.1.11 Phase 2 — Automation, Full Yedi & Polish

- Yedi enablement: UI/UX, tenant configuration, and the education compliance layer (DBS/safeguarding — mandatory gate).

- Payment automation (collection + payout); accounting export + credit notes.

- Automated ID / right-to-work verification; e-signature; in-app notification centre.

- Two-way ratings & feedback (client ↔ candidate) + reliability tracking → feeding matching.

- Referral programme; training/onboarding records (in-app).

- Geo / multi-slot adverts; reporting depth; full Yedi + education matching.

- Tidal client-visibility dashboard (“Tidal OS”: coverage / fill / spend / ratings).

## 2.2 Out-of-Scope Items

The following are excluded from this engagement and may be considered for future development:

- Native mobile app (separate track).

- Data migration beyond existing records.

- Third-party licence fees.

- Hosting and support after launch.

## 2.3 Dependencies and Assumptions

| # | Category | Description |
| --- | --- | --- |
| 1 | Access | Source code + Git access — the biggest variable: whether the empty modules hide a backend, and whether it is a single ENV-configured mono-repo or two drifting forks. |
| 2 | Scope | Candidate employment model (PAYE / umbrella / self-employed) — drives payslip and tax logic. |
| 3 | Scope | Adverts single-hire vs multi-slot — affects the booking/billing schema. |
| 4 | Scope | Whether a mobile app has already been released (marketing mentions an “OnDemand App”) — affects front-end scope. |
| 5 | Third-Party | Payment, SMS, ID-verification and e-sign services (e.g. GoCardless / Twilio / Yoti / DocuSign) — licence fees are client-borne. |
| 6 | Third-Party | Cloud infrastructure (AWS/GCP) costs are paid directly by the client. |
| 7 | Commercial | Phase 1 pricing is indicative at signature and confirmed during Sprint 1 (source-code audit), within (or below) the indicative ranges — no separate approval gate or pre-project phase. |
| 8 | Q&A | Questions and clarifications are answered within 2 working days. |

# 3. Solution Approach

## 3.1 Delivery Methodology

We employ an Agile Scrum methodology with 2-week sprints, following a “keep & extend” approach (no rebuild). Sprint 1 of Phase 1 includes the source-code audit: we review the repository, confirm reusability and validate the estimate in parallel with environment/CI setup and initial foundation work, then confirm pricing before Sprint 2 begins.

Key ceremonies:

- Sprint Planning — define the sprint backlog from prioritised user stories.

- Daily Standups — 15-minute sync on progress, blockers and next steps.

- Sprint Demo — bi-weekly client demonstration of working software.

- Sprint Retrospective — team reflection to improve the process.

## 3.2 Communication & Collaboration

| Tool / Activity | Purpose |
| --- | --- |
| Slack / Google Chat | Daily communication, real-time questions and updates |
| Jira | Project tracking, backlog, sprint progress, burn-down charts |
| GitHub / GitLab | Version control, pull-request reviews, automated CI/CD |
| Confluence / Google Docs | SRS, technical documentation, API specs, user guides |
| Figma | UI/UX design, interactive prototypes, design system |
| Telegram / Teams | Bi-weekly demos and reviews |

## 3.3 Quality Assurance Strategy

| Testing Type | Tools | Target / Approach |
| --- | --- | --- |
| Automated Testing | PHPUnit / Pest | Unit + feature tests on booking, billing and compliance logic |
| Integration Testing | QA Engineer | End-to-end portal flows (post → match → book → timesheet → invoice) |
| Manual / Exploratory | QA Engineer | Edge cases, RBAC, multi-tenant isolation, UX validation |
| User Acceptance | Staging environment | Client-led acceptance before go-live |

# 4. Technical Requirements

## 4.1 Core Architectural Principles

- Keep & extend the existing Laravel + Filament core — no rebuild.

- Shared multi-tenant backend; the industry layer is switched on/off via configuration.

- Per-tenant compliance isolation — Yedi safeguarding stays separate from Tidal.

- API-first services powering the Brand and Candidate self-service portals.

- Security and GDPR by design; automated tests and CI/CD from day one.

## 4.2 System Architecture

The system extends the existing admin into a layered, service-oriented platform:

- Client layer: Admin (Filament), Brand/School portal, Candidate/Teacher portal.

- API layer: REST services with multi-party JWT/session auth and RBAC.

- Service layer: Identity, Adverts, Applications/Matching/Booking, Compliance, Timesheets, Billing, Notifications, Multi-Tenancy.

- Data layer: MySQL/PostgreSQL (multi-tenant schema), Redis (cache/queue), S3-compatible document storage.

- External services: Email/SMS, payments, ID verification and e-signature (Phase 2).

## 4.3 Architecture Options — Shared vs Separate

Because every missing engine is identical for both platforms, we recommend building it once on a multi-tenant foundation:

| Scenario | Cost | Assessment |
| --- | --- | --- |
| A. Shared multi-tenant; industry-specific FE / branding / compliance | Lowest | RECOMMENDED — matches your instinct |
| B. Shared core library + two separate deployments | Medium | Versioning overhead; drift risk |
| C. Two fully separate products | Highest (+70–90%) | Not recommended — 2× maintenance |

## 4.4 Technical Configuration

| Category | Technology | Note |
| --- | --- | --- |
| Backend Framework | Laravel (PHP) | Existing core — keep & extend |
| Admin Panel | Filament 3.x | Existing admin — reuse & extend |
| Frontend (portals) | Livewire + Blade / Inertia | Brand & Candidate self-service portals |
| Database | MySQL 8 / PostgreSQL 14+ | Multi-tenant schema |
| Cache / Queue | Redis + Laravel Queue | Async billing, PDF, notifications |
| File Storage | S3-compatible | Documents, evidence, contracts, PDFs |
| Auth | Laravel + RBAC (2FA) | Multi-party auth; per-tenant roles |
| Notifications | Email (SES/SMTP) + SMS (Twilio) | Email-first + key SMS |
| Payments (Phase 2) | GoCardless / Stripe | Collection + payout |
| ID / Right-to-Work (Phase 2) | Yoti / similar | Automated verification |
| E-signature (Phase 2) | DocuSign / similar | Contracts |
| CI/CD | GitHub Actions / GitLab CI | Automated tests, build, deploy |
| Multi-Tenancy | Config-driven tenant + industry layer | White-label Yedi / Tidal |

# 5. Master Schedule

## 5.1 Master Schedule Overview

- Phase 1 (MVP): ~3 months (6 sprints)

Sprint 1 includes the source-code audit; delivery covers the full Tidal MVP and Tidal go-live on the shared multi-tenant foundation; enlarged parallel team.

- Phase 2 (Enhancement): ~1.5 months (3 sprints)

Full Yedi enablement (UI/UX, tenant configuration, DBS/safeguarding compliance layer) runs first, alongside payment automation, full education matching, ratings/referral/training and reporting depth; team continues at peak concurrency.

## 5.2 Phase 1 (MVP) Sprint Breakdown

| Sprint | Timeline | Key Activities |
| --- | --- | --- |
| Sprint 0 | Week 1–2 | Source-code audit (repo review, reusability confirmation, pricing confirmation) run in parallel with environment provisioning, CI/CD scaffolding, multi-tenant core and auth + RBAC scaffolding. |
| Sprint 1 | Week 3–4 | Identity/Auth/Access complete (2FA, reset, RBAC); Brand/School & Candidate/Teacher portal skeletons; Adverts & job lifecycle. |
| Sprint 2 | Week 5–6 | Candidate evidence upload + availability model; application persistence; core booking loop begins (Application → Matching). |
| Sprint 3 | Week 7–8 | Core booking loop complete (Offer/Accept → Booking) + basic clash detection; Compliance engine + right-to-work enforcement built in parallel. |
| Sprint 4 | Week 9–10 | Timesheets (shift → hours → pay basis); Billing (Invoice/Payslip generation + PDF + lifecycle); basic notifications (email-first + key SMS) — parallel streams. |
| Sprint 5 | Week 11–12 | Multi-tenant finalisation; security + GDPR baseline; automated tests + CI/CD; Tidal UAT; bug-fix |

## 5.3 Phase 2 (Enhancement) Sprint Breakdown

| Sprint | Timeline | Key Activities |
| --- | --- | --- |
| Sprint 1 | Week 1–2 | Yedi enablement: UI/UX, tenant configuration, and the education compliance layer (DBS/safeguarding mandatory gate); Yedi go-live prep. |
| Sprint 2 | Week 3–4 | Payment automation (collection + payout) + accounting export/credit notes; automated ID/right-to-work verification; e-signature. |
| Sprint 3 | Week 5–6 | In-app notification centre; two-way ratings & feedback + reliability tracking → matching; referral programme; training/onboarding records; geo/multi-slot adverts; reporting depth; full Yedi education matching; Tidal OS dashboard; UAT + deployment. |

# 6. Quotation & Work Breakdown Structure

## 6.1 Work Breakdown Structure

Domain

P1 Identity / Auth / Access

P2 Brand/School Portal

P3 Candidate/Teacher Portal

P4 Adverts / Job Lifecycle

P5 Applications / Matching / Booking (core)

P6 Compliance & Right-to-Work

P7 Timesheets & Attendance

P8 Billing (Invoice / Payslip)

P9 Payments & Settlement

P10 Notifications & Comms

P11 Documents / Contracts / E-sign

P12 Multi-Tenancy / White-Label

P13 Reporting & Analytics

P14 Non-Functional (security / GDPR / QA / CI-CD)

## 6.2 Team Structure & Cost Breakdown

We propose a fixed-scope, indicative-price model per phase. The ranges below reflect a hands-on but black-box assessment (no source-code access yet); Sprint 1 of Phase 1 (source-code audit + foundation) confirms or fine-tunes these figures within the first ~2 weeks of delivery — work continues without interruption, and any change is agreed before Sprint 2 rather than mid-project. Figures exclude hosting, third-party licences (e.g. Twilio / GoCardless / DocuSign / Yoti) and post-launch support.

6.2.1 Phase 1 (MVP) — ~3 months (Includes 2 weeks UAT)

| Position | M1 | M2 | M3 (0.5 month) | Total (M/M) | Unit Price (USD) | Total Cost (USD) |
| --- | --- | --- | --- | --- | --- | --- |
| PM | 1.5 | 1.0 | 0.5 | 3.0 | 3,600 | 10,800 |
| BA & UI/UX Designer | 1.5 | 1.0 | 0.5 | 3.0 | 3,000 | 9,000 |
| Senior Backend Engineer | 1.5 | 1.5 | 1.0 | 4.0 | 3,200 | 12,800 |
| Senior Frontend Engineer | 1.0 | 1.0 | 0.5 | 2.5 | 3,200 | 8,000 |
| DevOps Engineer | 0 | 0.5 | 0 | 0.5 | 3,400 | 1,700 |
| QC Engineer | 2.5 | 2.5 | 1.5 | 6.5 | 2,800 | 18,200 |
| TOTAL | 8.0 | 7.5 | 4.0 | 19.5 |  | $60,500 |

6.2.2 Phase 2 (Enhancement) — ~1.5 months

| Position | M1 | M2 (0.5 month) | Total (M/M) | Unit Price (USD) | Total Cost (USD) |
| --- | --- | --- | --- | --- | --- |
| PM | 1.5 | 0.5 | 2.0 | 3,600 | 7,200 |
| BA & UI/UX Designer | 1.5 | 0.5 | 2.0 | 3,000 | 6,000 |
| Senior Backend Engineer | 1.5 | 1.0 | 2.5 | 3,200 | 8,000 |
| Senior Frontend Engineer | 1.0 | 0.5 | 1.5 | 3,200 | 4,800 |
| DevOps Engineer | 0.5 | 0 | 0.5 | 3,400 | 1,700 |
| QC Engineer | 3.0 | 1.5 | 4.5 | 2,800 | 12,600 |
| TOTAL | 9.0 | 4.0 | 13.0 |  | $40,300 |

## 6.3 Payment Milestones

6.3.1 Phase 1 (MVP)

| Milestone | Deliverables | Percentage | Timeline |
| --- | --- | --- | --- |
| M1: Contract & Phase 0 | Signed SOW, fixed price issued, environment provisioned, foundation started | 50% | Upon execution |
| M2: Core Booking Demo | Auth + RBAC, portals, adverts, and core booking loop working | 20% | Week 6 |
| M3: UAT Start | Compliance, timesheets, billing and notifications complete; Tidal UAT | 20% | Week 10 |
| M4: UAT End | All bug fixed, documentation + source transfer | 10% | Week 12 |

6.3.2 Phase 2 (Enhancement)

| Milestone | Deliverables | Percentage | Timeline |
| --- | --- | --- | --- |
| M1: Kickoff | Scope confirmation, sprint planning; Yedi enablement started | 50% | Upon execution |
| M2: Yedi Enablement Demo | Yedi UI/UX, tenant configuration and education compliance layer (DBS/safeguarding) complete | 20% | Week 4 |
| M3: Full Feature & UAT Start | Payment automation, ID verification, e-sign, notification centre, ratings, referral, training, reporting, full Yedi education matching, Tidal OS | 20% | Week 5 |
| M4: Launch | All bugs fixed, documentation + source transfer | 10% | Week 6 |

Grand Total (Phase 1 + Phase 2): 32.5 M/M ~ $100,800

# 7. Future Enhancements Roadmap

The following are planned for future phases, subject to Phase 1–2 feedback and client priorities.

- Native mobile apps (candidate / brand) — separate track.

- Advanced matching (AI/ML ranking on reliability, distance and ratings).

- Analytics / BI depth — expansion of the “Tidal OS” coverage / fill / spend / ratings dashboards.

- Integrations marketplace (accounting, HR, background-check providers).

- Data migration tooling for historical records.

- Additional industry verticals on the same multi-tenant core.