PROPOSAL & INDICATIVE QUOTE

Yedi + Tidal Staffing Platform — From Admin Panel to Production Product

Prepared by: Sotatek   ·   Date: 2026-07-06   ·   Client proposal

Figures below are indicative estimates based on a direct, hands-on assessment of your live admin systems (black-box — without source-code access). They will be converted to a fixed price following a ~2-week Phase 0 audit.

1. Executive Summary

You have built a solid internal admin panel (Laravel + Filament) for a two-sided staffing platform. The data backbone — data model, admin CRUD, dashboard and system configuration — is real and reusable, representing roughly a quarter of a full platform. What remains is the transaction engine and the self-service surfaces that turn it into a sellable product.

Key finding: Yedi and Tidal are currently the SAME codebase — separately deployed, re-labelled (School/Teacher/Job vs Brand/Candidate/Advert) and configured per tenant.

Greenfield areas: candidate/client portals, the Booking entity, billing engine, timesheets, matching, compliance enforcement, RBAC and notifications are all still to be built.

Architecture recommendation: a shared multi-tenant backend with industry-specific front-end, branding and compliance layers — matching your own instinct, and ~40–45% cheaper than two separate builds.

We propose a “Keep & extend” approach (no rebuild), delivered in two tranches.

2. Current State — Directly Verified

We logged in and tested the live admin of both platforms directly (Tidal on 2026-06-29; Yedi + Tidal re-verification on 2026-07-03). The backbone is real and reusable:

Rich data model: Adverts (rate, charge %, shift, address, docs), Candidates (4-tab profile, references, compliance status, ID/video/contract storage), Brands/Schools, and System settings (charge, references, invoice bank/terms, contract template).

Working admin CRUD: full resource coverage, status filters, bulk actions and financial dashboard widgets.

Partial application logic: creating an Application correctly updates the related records (accepted-application, counters).

Per-tenant configuration: Yedi carries 5 education job-roles (QTS) plus a “DBS Evidence” catalogue; Tidal carries its charge defaults.

3. Gap to Production

Today's product is admin-only. The pieces that make it a transacting two-sided platform are not yet in place:

| Area | Current state (verified) | Gap |
| --- | --- | --- |
| Brand/School & Candidate/Teacher portals | No live front-end (app. = 403 placeholder) | Build two self-service portals |
| Core booking loop | Applications persist; no Booking entity / allocation / auto-status | Build matching → offer/accept → booking |
| Billing (invoice / payslip) | Template + bank config present; no generation engine | Build generation + PDF + lifecycle |
| Compliance / right-to-work | Evidence storage present; no rules / enforcement / capture | Build compliance engine + enforcement |
| Timesheets | None | Build shift → hours → pay basis |
| Auth & access | Admin login OK; no portal auth, no RBAC, no reset/2FA | Build multi-party auth + RBAC |
| Multi-tenancy (Tidal + Yedi) | Currently two forked deployments | Formalise multi-tenant white-label |
| Payments / Notifications / E-sign / Reporting | Minimal or none | Build per tranche |

Across ~110 features assessed: ~23 done, ~41 partial, ~46 missing.

Goodwill note: during the assessment we identified a production bug — Declaration creation fails on upload (Livewire) — present on both platforms (shared code). We are happy to share the details at no charge.

4. Architecture Recommendation — Shared vs Separate

Because every missing engine is identical for both platforms, we recommend building it once on a multi-tenant foundation, switching the industry layer on/off via configuration. Industry compliance is separated through per-tenant rules (Yedi safeguarding stays isolated from Tidal beauty).

| Scenario | Cost | Assessment |
| --- | --- | --- |
| A. Shared multi-tenant; industry-specific FE / branding / compliance | Lowest | RECOMMENDED — matches your instinct |
| B. Shared core library + two separate deployments | Medium | Versioning overhead; drift risk |
| C. Two fully separate products | Highest (+70–90%) | Not recommended — 2× maintenance |

5. Scope

Tranche 1 — MVP launch (Tidal)

Auth + RBAC · Brand/School portal (post/manage requests, review applicants, booking, invoice view) · Candidate/Teacher portal (onboarding, upload evidence, set availability, search, apply, accept, timesheet, payslip) · Core booking loop (Application → Matching → Offer/Accept → Booking) · Availability model + basic clash detection · Compliance engine + enforcement · Timesheets · Invoice/Payslip generation (PDF) · Basic notifications (email-first + key SMS: booking/timesheet/compliance) · Multi-tenant foundation · Security + GDPR baseline + automated tests + CI/CD · Tidal go-live. Yedi is enabled immediately after via configuration plus the education compliance layer (DBS/safeguarding — a mandatory gate).

Tranche 2 — Automation + full Yedi + polish

Payment automation (collection + payout) · Automated ID / right-to-work verification · E-signature · In-app notification centre · Two-way ratings & feedback (client ↔ candidate) + reliability tracking → feeding matching · Referral programme · Training/onboarding records (in-app) · Accounting export + credit notes · Geo / multi-slot adverts · Reporting depth · Full Yedi + education matching · Tidal client-visibility dashboard (“Tidal OS”: coverage / fill / spend / ratings).

Out of scope (this engagement)

Native mobile app (separate track), data migration beyond existing records, third-party licence fees, and hosting/support after launch.

6. Effort & Timeline (bottom-up, per feature, 14 domains)

| Domain | Full (md) | MVP (md) |
| --- | --- | --- |
| P1 Identity / Auth / Access | 36 | 27 |
| P2 Brand/School Portal | 56 | 48 |
| P3 Candidate/Teacher Portal | 67 | 59 |
| P4 Adverts / Job Lifecycle | 41 | 26 |
| P5 Applications / Matching / Booking (core) | 59 | 52 |
| P6 Compliance & Right-to-Work | 48 | 41 |
| P7 Timesheets & Attendance | 35 | 27 |
| P8 Billing (Invoice / Payslip) | 55 | 46 |
| P9 Payments & Settlement | 32 | 8 |
| P10 Notifications & Comms | 27 | 14 |
| P11 Documents / Contracts / E-sign | 30 | 19 |
| P12 Multi-Tenancy / White-Label | 39 | 29 |
| P13 Reporting & Analytics | 25 | 7 |
| P14 Non-Functional (security / GDPR / QA / CI-CD) | 68 | 59 |
| Development subtotal | 618 | 462 |
| + Overlay (discovery/audit, UI-UX, foundation) | 50 | 50 |
| + PM + contingency (included) | — | — |
| TOTAL (rounded) | ~870 | ~660 |

PM and contingency are already included in the totals. Yedi education delta: +40–70 md beyond the baseline. Proposed team of ~6 (1 Tech Lead/BE, 2 BE, 2 FE, 1 QA, plus part-time PM and UI/UX).

7. Indicative Quote

| Item | Effort | Timeline | GBP | USD |
| --- | --- | --- | --- | --- |
| Tranche 1 — MVP launch (Tidal, shared) | ~660 md | ~6.5–7.5 months | ~£125k–156k | ~$158k–198k |
| + Yedi education delta | +40–70 md | +0.5–1 month | ~£8k–17k | ~$10k–21k |
| Enhancement (Tranche 2) | ~210 md | ~+3 months | ~£40k–50k | ~$50k–63k |
| Full production-grade (both platforms) | ~870 md | ~8.5–10 months | ~£165k–206k | ~$209k–261k |

Indicative ranges; a fixed price will be issued after Phase 0 and will fall within (or below) these ranges. Excludes hosting, third-party licences (e.g. Twilio / GoCardless / DocuSign / Yoti) and post-launch support.

8. Commercial Model — Audit-first (de-risks both sides)

We have assessed the running system but have not yet reviewed the source code. To protect both parties:

Phase 0 — Discovery & code audit (~2 weeks): review the repository, confirm reusability and validate the estimate (fixed price).

Fixed price for Tranche 1: issued at the end of Phase 0, within (or below) the ranges above.

This gives you a fair, accurate price up front, with no mid-project surprises for either side.

9. Assumptions & Dependencies to Confirm

Source code + Git access — the biggest variable: whether the empty modules hide a backend, and whether it is a single ENV-configured mono-repo or two drifting forks.

Candidate employment model (PAYE / umbrella / self-employed) — drives payslip and tax logic.

Adverts single-hire vs multi-slot — affects the booking/billing schema.

Whether a mobile app has already been released (your marketing mentions an “OnDemand App”) — affects front-end scope.

10. Next Steps

Approve Phase 0 (audit).

Provide source code + Yedi/Tidal access; confirm the points in Section 9.

Sotatek issues a fixed price for Tranche 1 within ~2 weeks.

Appendices available on request: 14-domain gap analysis (EN + VI), black-box test pack (47 screenshots), per-feature effort WBS, requirements traceability matrix, and the Yedi↔Tidal cross-comparison.