Project Proposal

YEDI + TIDAL

Staffing & Compliance Platform — MVP & Phase 2

Flutter Mobile (iOS & Android) + Laravel / Filament Web Admin

Version: v1.0

Authored by: Sotatek — Client Delivery

Approved by: ______________________

United Kingdom, July 2026

| Presenter | Position | Division |
| --- | --- | --- |
| [Presenter Name] | Project Lead | Sotatek — Client Delivery |

Edit History

| Date | Version | Description | Editor |
| --- | --- | --- | --- |
| July 8, 2026 | 1.0 | Create | Sotatek |

Approval

| Approved date | Version | Approved by | Position |
| --- | --- | --- | --- |
|  | 1.0 |  |  |

Table of Contents

# 1. Project Overview

Yedi and Tidal are two staffing brands operated on one shared platform connecting advertisers (schools, care settings, brands, and employers) with applicants (workers) for short-notice and planned assignments. Yedi serves the education and safeguarding-regulated segment, where placement is gated on Disclosure and Barring Service (DBS) checks and other compliance credentials; Tidal serves the broader beauty, retail, and events staffing market. This proposal covers the work to take the client's existing codebase from its current state to a production-ready Minimum Viable Product that both brands can launch on together, plus a costed Phase 2 enhancement roadmap.

This is a brownfield engagement. A source-code audit (July 2026) confirmed the existing Laravel back end and Flutter mobile apps are substantially built — the applicant and advertiser apps are shipped, and the application lifecycle, compliance onboarding, and document-generation billing already work. The scope is therefore a gap-and-hardening build — reusing what is sound and closing correctness, security, compliance, and reliability gaps — rather than a rebuild.

## Core Business Challenge

- Not yet launch-ready: gaps in payments integrity, billing correctness, and reliability must be closed before real money and real placements flow through the platform.

- Compliance is a hard requirement, not a feature: for Yedi, an applicant must not be bookable into a safeguarding-regulated role with an expired or missing DBS/credential — this enforceable gate does not yet exist in structured form.

- Billing is disconnected from actual work: charge and pay are driven by scheduled shift times, not approved timesheet hours, creating dispute and revenue-leakage risk.

- Dual-brand launch: Yedi and Tidal must run on one platform with brand-specific policy (compliance, payroll, matching) resolved per brand.

- Regulatory exposure: GDPR obligations (account deletion, data export, right to erasure, consent) and correct UK payroll (umbrella/PAYE) are legal must-haves for a UK launch.

## Solution Value Proposition

- Trustworthy money flow: idempotent billing, validated charge/pay bounds, and correct payslip/invoice generation driven by approved hours.

- Enforceable compliance: structured DBS/credential records with expiry logic that automatically block non-compliant bookings for Yedi.

- Timesheet-to-billing rewire: workers submit timesheets, advertisers approve them, and billing is triggered off approved hours.

- Integrated umbrella payroll: assignment hours, rates, and dates are fed to an umbrella payroll provider, with payslip display and AWR tracking.

- A launch-safe platform: security hardening, GDPR compliance, observability, a test/CI baseline, and the cross-cutting UX a live app needs.

## Project Objectives

- Deliver a production-ready MVP that Yedi and Tidal can launch on together, on the existing Flutter + Laravel stack.

- Close all identified security, GDPR, payments-integrity, and reliability gaps ahead of commercial launch.

- Implement multi-headcount booking, availability, and ranked matching so advertisers can fill and cover assignments efficiently.

- Stand up the DBS/safeguarding compliance gate as a first-class, enforceable part of the Yedi booking flow.

- Integrate umbrella payroll and rewire billing to approved timesheet hours.

- Establish a brand-policy layer so both brands share one platform while differing on compliance, payroll, and matching rules.

# 2. Project Scope

## 2.1 In-Scope — MVP (Phase 1)

The MVP is organised into nine capability workstreams (A–I). Because this is a hardening-and-gap build, workstreams are grouped by capability rather than by end-user surface.

| Workstream | Scope |
| --- | --- |
| A. Platform Hardening & Security | Auth hardening (rate limiting, token revoke/rotation, secure token storage, 401 handling); fine-grained RBAC; secrets rotation/CORS; GDPR — account deletion, data export (SAR), right to erasure, PII scrubbing, consent. |
| B. Payments Integrity & Reliability | Billing correctness and charge/rate-bounds validation; idempotency (unique constraints, single-server scheduling, job retry); reliability/observability (crash reporting, backups, monitoring); DB integrity (money as minor-unit + currency, index/FK fixes); test-harness and CI/CD baseline. |
| C. Booking & Allocation | Multi-headcount booking: per-person booking model, partial-fill advert status, accept-to-booking allocation, advert editing, and applicant/advertiser booking views. |
| D. Timesheet & Billing Rewire | Timesheet capture and approval (submit/approve/dispute/query) with applicant and advertiser UI; billing rewired to approved hours with real gross/net payslip generation. |
| E. Availability & Matching | Availability model, picker UI, double-booking guard; ranked candidate suggestions scored on compliance, availability, and proximity, with an advertiser suggestions UI. |
| F. Compliance — Yedi DBS / Safeguarding | Structured compliance-credential records (DBS number/level/dates, QTS), expiry columns and admin entry; automatic compliance-status computation, scheduled expiry, booking gate by expiry, and applicant warnings. |
| G. Payroll (Umbrella) | Umbrella provider connector, assignment-data feed (hours/rate/dates), payslip proxy and display, worker onboarding handoff, and AWR 12-week tracking. |
| H. Reporting & Brand-Policy | CSV export, client dashboard (fill-rate/spend/cover) and admin report widgets; brand-policy layer and configuration resolver for Yedi vs Tidal differences. |
| I. Cross-Cutting UX & Platform | Search and filtering, empty/error/loading states, onboarding/first-run, notification preferences, pagination, offline handling; internationalisation/timezone, force-update/version gate, accessibility, and analytics. |

## 2.1.10 Phase 2 — Enhancement Roadmap (costed)

Phase 2 is scoped and costed in this proposal (Sections 6.1–6.3) as a separate tranche, to be commissioned after MVP launch.

| Workstream | Scope |
| --- | --- |
| P2-A. Scale & Operations | Horizontal scaling (stateless app, shared cache, load balancer, distributed scheduler); admin impersonation/support tooling, maintenance mode, demo/seed environments; anti-virus scanning of uploads. |
| P2-B. Revenue & Payments | Refunds/adjustments/credit notes and dispute handling; in-house PAYE payroll (tax/NI, HMRC RTI, pension auto-enrolment, holiday pay); additional payroll providers; multi-currency. |
| P2-C. Growth & Intelligence | Automated matching engine and learning from placement outcomes; predictive staffing demand; advanced analytics/BI dashboards; ratings depth, referral programme, in-app training, worker rewards, calendar integration. |
| P2-D. Advanced Compliance & Talent | Full DBS engine (DBS Update Service API, barred-list, automated reminders); talent pools by city/brand; client self-serve booking; additional brand onboarding. |

## 2.2 Out-of-Scope Items (MVP)

- All Phase 2 items above are out of the MVP fixed price and quoted separately.

- Native (non-Flutter) rewrites and new third-party integrations beyond the umbrella payroll provider.

- Cloud infrastructure costs and third-party service fees (umbrella provider, FCM, maps, crash reporting) — paid directly by the client.

- Architecture discovery and DevOps/environment setup are treated as pre-project activities and are not itemised in the quotation.

## 2.3 Dependencies and Assumptions

| # | Category | Description |
| --- | --- | --- |
| 1 | Baseline codebase | Reuse of the client's existing Laravel and Flutter code. Scope is the gap-and-hardening build, not a rewrite. Material undisclosed defects may change scope. |
| 2 | Umbrella payroll API | Access, credentials, and API contract for the umbrella provider must be supplied by the client. External dependency and key schedule risk. |
| 3 | Currency | Figures are in USD per the internal rate card. GBP conversion at the prevailing rate to be confirmed before contracting. |
| 4 | Man-month basis | One man-month = 20 working days (locked with client, 2026-07-08). |
| 5 | Joint launch | Yedi and Tidal launch together; the DBS/safeguarding gate is in the MVP. |
| 6 | Deployment | A single application server is assumed for the MVP; multi-server scaling is Phase 2. |
| 7 | Delivery efficiency | Man-days reflect AI-assisted development plus a client-directed 30% acceleration to hit a 1.5–2 month MVP; correctness-critical work carries lower reduction. |

# 3. Solution Approach

## 3.1 Delivery Methodology

Delivery follows two-week agile sprints with fixed scope per sprint. As a brownfield engagement, Sprint 1 establishes a safety net before feature work: a test-harness bootstrap and CI/CD pipelines so every subsequent change to the existing code is validated automatically. Work then respects the platform's critical dependencies — idempotency and timesheet capture land before the billing rewire; the compliance model lands before the booking gate that depends on it.

- Sprint 1: test harness, CI/CD, and the security-hardening baseline.

- Incremental hardening: each workstream delivered behind tests; correctness-critical paths given extra review.

- Demonstrable increments: a working, demoable build at each milestone rather than a big-bang delivery.

- Source-code ownership transferred to the client on completion.

## 3.2 Communication & Collaboration

| Activity | Cadence | Participants |
| --- | --- | --- |
| Sprint planning | Every 2 weeks | PM, tech lead, client product owner |
| Progress stand-up / update | Weekly | Delivery team + client PO |
| Sprint demo & review | End of each sprint | Full team + client stakeholders |
| Milestone sign-off | At each milestone | PM + client approver |
| Ad-hoc risk escalation | As needed | PM + client PO |

## 3.3 Quality Assurance Strategy

Testing is budgeted at 30% of total effort, reflecting the correctness-critical nature of a payments-and-compliance platform. QA focuses where defects are most costly:

| Area | Focus |
| --- | --- |
| Payments integrity | Idempotency under retries; charge/rate-bounds; invoice/payslip correctness; money-column migration reconciliation. |
| Compliance gate | Expired/missing DBS correctly blocks Yedi bookings; status auto-computation and scheduled expiry verified. |
| Timesheet-to-billing | Approved hours drive billing; dispute/query paths; no double-billing. |
| Umbrella payroll | Correct assignment feed, payslip proxy, AWR tracking; failure/retry against the external API. |
| Regression & CI | Automated suite gates every merge; brownfield changes validated against existing behaviour. |

# 4. Technical Requirements

## 4.1 Core Architectural Principles

- Reuse over rewrite: build on the existing Laravel + Flutter codebase; refactor only where correctness, security, or compliance require it.

- Correctness-critical by design: money as integer minor units + currency; billing idempotent; compliance enforced at the policy layer, not the UI.

- Brand-policy driven: a single platform resolves compliance, payroll, and matching rules per brand from a configuration layer.

- Observable and recoverable: crash reporting, monitoring/alerts, backups, and queue retry/backoff as first-class concerns.

## 4.2 System Architecture (MVP target)

Yedi + Tidal — Proposal MVP architecture (grey = reuse, blue = new build, orange = hardening)

Core data flow: Advert to Booking to Timesheet to Billing to Payroll

## 4.3 Technical Configuration

| Category | Technology | Note |
| --- | --- | --- |
| Mobile | Flutter (Dart) | Existing apps; iOS & Android. |
| Back end | Laravel 11 (PHP) | Existing API; Filament 3 admin. |
| Queues / jobs | Laravel Horizon + Redis | Scheduling, retries, background jobs. |
| Auth / RBAC | Laravel Sanctum + role/permission layer | Fine-grained policies (added). |
| Payroll integration | Typed HTTP connector (Saloon) | Umbrella provider (external API). |
| Notifications | Firebase FCM | Push + preferences/opt-out. |
| Observability | Sentry + Crashlytics + monitoring | Alerts, backups, queue metrics. |
| Database | MySQL 8 | Confirmed on the baseline (49 migrations). |

# 5. Master Schedule

## 5.1 Overview

- MVP effort: ~197 man-days (AI-assisted, 30% acceleration applied), $29,526 before contingency.

- MVP duration: ~1.5–2 months, delivered by a parallel team across 4 two-week sprints (upper bound shown).

- Phase 2 effort: ~163 man-days, $24,496 before contingency — scoped as a separate tranche.

- Sequencing: quality baseline first; idempotency and timesheet before billing rewire; compliance model before the booking gate.

## 5.2 MVP Sprint Breakdown

| Sprint | Timeline | Key Activities |
| --- | --- | --- |
| Sprint 1 | Weeks 1–2 | Test-harness + CI/CD; security hardening (rate-limit, token rotation, secure storage, RBAC, secrets/CORS); GDPR (deletion, export, erasure, consent); idempotency + DB integrity + money-column refactor. |
| Sprint 2 | Weeks 3–4 | Payments integrity (payslip/invoice, retries); multi-headcount booking (model, partial-fill, allocation, views); timesheet capture. |
| Sprint 3 | Weeks 5–6 | Billing rewire to approved hours + real payslips; availability (model, picker, guard); compliance (DBS model, enforcement, booking gate); ranked matching. |
| Sprint 4 | Weeks 7–8 | Umbrella payroll integration; reporting & brand-policy; cross-cutting UX/platform; UAT and launch hardening. |

A 1.5-month (3-sprint) plan is achievable with higher parallelism; the 4-sprint plan above is the upper bound. The critical path (timesheet to billing rewire; compliance model to gate) is the main constraint on further compression.

# 6. Work Breakdown Structure & Quotation

## 6.1 Quotation Summary

Fixed Price for the defined MVP scope: complete development, QA/testing, and source-code ownership transfer on completion. A 12% contingency reflects brownfield risk and the external umbrella-payroll dependency. Figures in USD (see Assumptions).

| Scope | Effort (md) | Development | Fixed Price (incl. 12%) |
| --- | --- | --- | --- |
| MVP (Phase 1) | 197 | $29,526 | $33,069 |
| Phase 2 (enhancement) | 163 | $24,496 | $27,436 |
| Combined | 360 | $54,022 | $60,505 |

Note: Cloud infrastructure and third-party service fees (umbrella provider, FCM, maps, crash reporting) are not included and are paid directly by the client.

## 6.2 Work Breakdown Structure

6.2.1  Phase 1 (MVP)

| EPIC | Feature | Sub-Feature | Function | Notes |
| --- | --- | --- | --- | --- |
| A. Platform Hardening & Security | Authentication & Access | Auth hardening | Rate limiting (login/forgot-pw/signed form) |  |
|  |  |  | Token revoke + rotation endpoint |  |
|  |  |  | Secure token storage (Keychain/Keystore) |  |
|  |  |  | Session 401 handling + refresh |  |
|  |  | Authorization | Fine-grained RBAC (spatie roles/permissions) |  |
|  |  |  | Policy coverage audit + gaps |  |
|  | Secrets & Config | Config hardening | Rotate + externalize Maps/Firebase keys |  |
|  |  |  | CORS configuration |  |
|  |  |  | .env.example + secrets management |  |
|  | GDPR & Privacy | Account lifecycle | Account deletion (self-serve, cascade/anonymize) |  |
|  |  |  | Account deactivation / reactivation |  |
|  |  | Data rights | SAR data export (per-user) |  |
|  |  |  | Right to erasure + retention policy jobs |  |
|  |  |  | PII scrubbing in logs/audits |  |
|  |  |  | Consent + Terms/Privacy acceptance |  |
| B. Payments Integrity & Reliability | Billing correctness | Payslip & invoice | Fix payslip stub (fields + template) |  |
|  |  |  | Charge %/rate bounds validation |  |
|  |  | Idempotency | Unique constraints (invoices/payslips per booking) |  |
|  |  |  | Scheduler onOneServer + withoutOverlapping |  |
|  |  |  | Job retry/backoff/failed handling |  |
|  | Reliability & Infra | Observability | Crash reporting (Sentry + Crashlytics on) |  |
|  |  |  | Backup + monitoring/alerts setup |  |
|  |  |  | Horizon retry / queue tuning |  |
|  |  | DB integrity | money -> 2-column refactor (amount_minor+currency) | Live-data migration: backfill |
|  |  |  | Indexes + FK + soft-delete cascade fixes |  |
|  | Quality baseline | Test & CI | Test harness bootstrap (factories/fixtures) |  |
|  |  |  | CI/CD pipelines (2 repos) |  |
| C. Booking & Allocation | Multi-headcount booking | Booking entity | Booking model + migration (per-person) |  |
|  |  |  | AdvertStatus refactor (partial-fill) |  |
|  |  |  | Accept -> create Booking + allocation |  |
|  |  | Advert management | Advert edit/update (API + admin) |  |
|  |  |  | Headcount N on advert (create/list UI) |  |
|  |  | Booking views | Applicant booking views (per-person) |  |
|  |  |  | Advertiser booking / coverage views |  |
| D. Timesheet & Billing Rewire | Timesheet | Capture | Timesheet model + enum + migration |  |
|  |  |  | SubmitTimesheet handler + API |  |
|  |  |  | Applicant submit timesheet UI |  |
|  |  | Approval | Approve/Dispute/Query handlers |  |
|  |  |  | Advertiser approve timesheet UI |  |
|  | Billing rewire | Billing from actual hours | Rewire charge/pay to approved hours | Critical path (after Timesheet) |
|  |  |  | Trigger change (approved gate, not ends_at) |  |
|  |  |  | Payslip real (gross/net) generation |  |
| E. Availability & Matching | Availability | Availability model | Availability model + API |  |
|  |  |  | Availability picker UI |  |
|  |  |  | Double-booking guard |  |
|  | Matching | Ranked suggestions | Ranked scoring (compliant+avail+proximity) | Correctness-critical |
|  |  |  | Suggested-candidates UI (advertiser) |  |
| F. Compliance (Yedi DBS/Safeguarding) | Structured credentials | Credential model | compliance_credentials model+enum+migration |  |
|  |  |  | Typed fields (DBS number/level/dates, QTS) |  |
|  |  |  | Expiry columns + admin entry (Filament) |  |
|  |  | Enforcement | Auto-compute compliance status | Safeguarding — critical |
|  |  |  | ExpireCredentials scheduled command |  |
|  |  |  | Booking gate by expiry (AdvertPolicy) | Blocks non-compliant Yedi bookings |
|  |  |  | Compliance warnings UI (applicant) |  |
| G. Payroll (Umbrella) | Umbrella integration | Connector | PayrollProvider connector (typed HTTP) | External umbrella API |
|  |  |  | Feed assignment data (hours/rate/dates) |  |
|  |  |  | Payslip proxy + display |  |
|  |  | Compliance | Worker umbrella onboarding handoff |  |
|  |  |  | AWR 12-week tracking |  |
| H. Reporting & Brand-Policy | Reporting | Reports | Export API (CSV) |  |
|  |  |  | Client dashboard (fill-rate/spend/cover) |  |
|  |  |  | Admin report widgets |  |
|  | Brand-policy & multi-tenant | Policy layer | Brand-policy DB layer (Settings ext) |  |
|  |  |  | Config resolver (compliance/payroll/matching) |  |
| I. Cross-Cutting UX & Platform | UX completeness | States & search | Search & filter (adverts/candidates) |  |
|  |  |  | Empty / error / loading states (all screens) |  |
|  |  |  | Onboarding / first-run / tutorials |  |
|  |  |  | Notification preferences / opt-out |  |
|  |  |  | Pagination / infinite scroll |  |
|  |  |  | Offline handling + connectivity |  |
|  |  | Platform | i18n / timezone handling |  |
|  |  |  | App force-update / version gate |  |
|  |  |  | Accessibility (a11y) pass |  |
|  |  |  | Analytics / event tracking |  |

6.2.2  Phase 2

| EPIC | Feature | Sub-Feature | Function | Notes |
| --- | --- | --- | --- | --- |
| P2-A. Scale & Operations | Horizontal scaling | Multi-instance | Stateless app + shared session/cache |  |
|  |  |  | Load balancer + health/readiness probes |  |
|  |  |  | Distributed scheduler / leader-election |  |
|  |  |  | Multi-instance queue tuning |  |
|  | Ops tooling | Support | Admin impersonation / support login |  |
|  |  |  | Maintenance mode |  |
|  |  |  | Demo / seed-data environments |  |
|  |  |  | AV scanning of uploads (ClamAV integration) |  |
| P2-B. Revenue & Payments | Adjustments | Corrections | Refunds / adjustments / credit notes |  |
|  |  |  | Dispute / chargeback handling |  |
|  | Payroll expansion | In-house PAYE | PAYE engine (income tax + NI calc) | In-house payroll |
|  |  |  | RTI submission (HMRC FPS/EPS) | HMRC integration |
|  |  |  | Pension auto-enrolment |  |
|  |  |  | Holiday pay accrual |  |
|  |  | Providers | Additional umbrella/payroll providers |  |
|  | Multi-currency | Currency | Multi-currency support |  |
| P2-C. Growth & Intelligence | Smart matching | Automation | Automated matching engine (scoring + auto-offer) |  |
|  |  |  | Learning from placement outcomes |  |
|  |  |  | Predictive staffing demand |  |
|  | Analytics & BI | Dashboards | Advanced analytics / BI dashboards |  |
|  |  |  | Regional performance dashboards |  |
|  |  |  | Candidate performance scoring |  |
|  | Engagement | Worker features | Ratings depth / 2-way feedback |  |
|  |  |  | Referral programme |  |
|  |  |  | In-app training / onboarding modules |  |
|  |  |  | Worker rewards |  |
|  |  |  | Calendar integration |  |
| P2-D. Advanced Compliance & Talent | Full DBS engine | Automation | DBS Update Service API integration |  |
|  |  |  | Barred-list check |  |
|  |  |  | Automated compliance reminders |  |
|  | Talent | Pools & self-serve | Talent pools by city/brand |  |
|  |  |  | Client self-serve booking |  |
|  |  |  | Additional brand onboarding (multi-tenant) |  |

## 6.3 Team Structure & Cost Breakdown

Effort in person-months (one man-month = 20 working days). Unit prices (USD) are the internal rate card; confirm before contracting.

MVP (Phase 1)

| Position | Person-months | Unit Price (USD/mo) | Total Cost (USD) |
| --- | --- | --- | --- |
| Project Manager | 0.98 | $3,600 | $3,528 |
| BA & UI/UX Designer | 0.98 | $3,000 | $2,940 |
| Backend Engineer | 2.93 | $3,000 | $8,790 |
| Mobile Engineer (Flutter) | 1.49 | $3,000 | $4,470 |
| Frontend Engineer (Web) | 0.50 | $3,000 | $1,500 |
| QC Engineer | 2.95 | $2,800 | $8,260 |
| TOTAL | 9.83 |  | $29,526 |

Development $29,526  +  Brownfield contingency 12% $3,543  =  MVP Fixed Price $33,069

Phase 2 (enhancement tranche)

| Position | Person-months | Unit Price (USD/mo) | Total Cost (USD) |
| --- | --- | --- | --- |
| Project Manager | 0.82 | $3,600 | $2,952 |
| BA & UI/UX Designer | 0.82 | $3,000 | $2,460 |
| Backend Engineer | 2.94 | $3,000 | $8,820 |
| Mobile Engineer (Flutter) | 0.68 | $3,000 | $2,040 |
| Frontend Engineer (Web) | 0.47 | $3,000 | $1,410 |
| QC Engineer | 2.45 | $2,800 | $6,860 |
| TOTAL | 8.18 |  | $24,496 |

Development $24,496  +  contingency 12% $2,940  =  Phase 2 Fixed Price $27,436

## 6.4 Payment Milestones (MVP)

Milestone amounts are a fixed percentage of the MVP fixed price ($33,069).

| Milestone | Deliverables | % | Amount |
| --- | --- | --- | --- |
| M1: Contract Signing | Signed SOW; Sprint 1 initiated — test harness, CI/CD, security baseline; umbrella-payroll API discovery. | 40% | $13,228 |
| M2: Core Demo (Wk 4) | Payments integrity, multi-headcount booking, and timesheet capture on a hardened build. | 30% | $9,921 |
| M3: UAT & Beta (Wk 6) | Billing rewire, availability/matching, compliance gate and umbrella payroll; internal QA passed; beta deployed. | 20% | $6,614 |
| M4: Production Launch (Wk 8) | Reporting & brand-policy and cross-cutting UX complete; UAT resolved; documentation and source-code transfer. | 10% | $3,307 |

Phase 2 milestones are agreed when the tranche is commissioned; indicative split 40% / 40% / 20% of the Phase 2 fixed price ($27,436).

# 7. Future Enhancements Roadmap

Beyond Phase 2, candidate enhancements (not costed here) include:

- AI-assisted matching that learns from placement outcomes and predicts staffing demand.

- Deeper workforce analytics and BI across regions, brands, and cohorts.

- Client self-serve booking and dynamic rate management.

- Onboarding of additional brands onto the shared brand-policy platform.

# 8. Q&A Clarifications

Q1. Which currency is the quotation in?

Figures are in USD per the internal rate card. A GBP figure at the prevailing exchange rate will be confirmed before contracting; the platform itself transacts in GBP.

Q2. What does the 12% contingency cover?

Brownfield risk (the baseline's full state is confirmed in Sprint 1) and the external umbrella-payroll dependency. It is included in the fixed price.

Q3. How was 1.5–2 months achieved for the MVP?

Bottom-up estimate per function, AI-assisted, plus a client-directed 30% delivery-efficiency acceleration and a parallel team. Correctness-critical work keeps a lower reduction; the schedule assumes a clean baseline and prompt umbrella-API access.

Q4. Are file uploads virus-scanned?

Not in the MVP. Uploads currently have no AV scanning; it is recommended and included in Phase 2 (or can be pulled into the MVP on request).

Q5. Are refunds/credit notes included?

No — they are Phase 2 (Revenue & Payments). If required for launch they can be added, affecting effort and price.

Q6. What is the umbrella-payroll dependency?

API access, credentials, and a documented contract from the umbrella provider — external and the single largest schedule risk. Sprint 1 includes a discovery step.

Q7. Why single app-server for the MVP?

Sufficient for expected launch load and keeps the scheduler/queue model simple (single-server scheduling supports idempotent billing). Horizontal scaling is Phase 2.

Q8. How was the estimate produced?

Per function as AI-assisted coding man-days across Backend, Mobile, and Web, expanded via a fixed 10/10/50/30 ratio (Spec / PM / Coding / Testing), with AI reductions by task type and a 30% delivery-efficiency factor.

End of Document