## README
Yedi + Tidal — MVP & Phase 2 Work Breakdown Structure (WBS)
Internal - Sotatek presale - source-grounded (audit Jul 8) - formula-driven, recalcs from the Rates sheet.
STRUCTURE: Phase (MVP / Phase 2) -> EPIC -> Feature -> Sub-Feature -> Function. Each function = base CODING md per discipline (Backend/Mobile/Web).
MODEL (all formula-driven):
1. Base Coding = BE + Mobile + Web (raw, pre-AI).
2. AI Reduction % per Task Type ('AI Factors') -> Adjusted Coding.
3. Delivery Efficiency factor (Rates!B21 = 0.70) applied = client-directed 30% compression on top of AI-assist.
4. Effort ratio 10/10/50/30: Total = Adjusted Coding / 50% x Efficiency. Spec=10%, PM=10%, Testing=30% derived from Total.
5. Cost = Coding x Dev-rate + Spec x BA + PM x PM + Testing x QC (day-rate = monthly / man-month days).
6. Contingency % added on Summary for grand total.
RISK NOTE on the 0.70 efficiency factor:
The 30% reduction is a business-directed compression requested to hit a 1.5-2 month MVP. It is ON TOP of AI-assisted reductions already baked into 'AI Factors'.
It assumes a senior, highly-parallel team and clean baseline. It increases schedule and quality risk on correctness-critical work (payments, compliance, payroll). The 12% contingency only partially offsets. Recommend a sensitivity view at factor = 0.85 before contracting.
TIMELINE TARGET: MVP ~1.5-2 months (3-4 two-week sprints) with a larger concurrent team. Phase 2 scoped separately (roadmap).
ASSUMPTIONS (locked 2026-07-08): man-month = 20 days; umbrella payroll; Yedi+Tidal joint launch (DBS in MVP); multi-headcount; single app-server (MVP); GBP; baseline = reuse client code.
SHEETS: Rates ¦ AI Factors ¦ WBS ¦ Summary ¦ Missing-Features Checklist ¦ Self-Review

## Rates
RATES & GLOBAL INPUTS (edit yellow cells)
Man-month (working days) | 20
Role monthly rate |  | Day-rate (=monthly/MM)
Developer (BE/Mobile/Web) | 3000
QC | 2800
Project Manager | 3600
BA & Designer | 3000
DevOps | 3400
Effort ratio
Spec % | 10%
PM % | 10%
Coding % | 50%
Testing % | 30%
Ratio check
Contingency % | 12%
Delivery Efficiency factor | 0.7
(1.00 = no cut; 0.70 = -30% client-directed)

## AI Factors
AI-Assisted Development - Effort Reduction by Task Type
Task Type | AI Reduction % | Rationale
CRUD/Config | 45% | Boilerplate CRUD/config/scaffolding - highest AI leverage.
UI Standard | 40% | Standard screens/forms/lists - strong AI leverage.
Data/Migration | 35% | Schema/migrations/model wiring - good AI leverage.
Infra/DevOps | 30% | CI/CD, queue, monitoring - moderate; environment-specific.
Business Logic | 30% | Domain rules/handlers - moderate; human design + validation.
Integration | 25% | 3rd-party (umbrella/FCM/HMRC) - lower; external contracts + testing.
Complex/Critical | 15% | Payments, idempotency, compliance/matching/PAYE - lowest; correctness-critical.

## WBS
Phase | EPIC | Feature | Sub-Feature | Function | Task Type | BE | Mobile | Web | Base Coding | AI Red.% | Adj Coding | Total (md) | Coding (md) | Spec (md) | PM (md) | Testing (md) | Cost
MVP | A. Platform Hardening & Security | Authentication & Access | Auth hardening | Rate limiting (login/forgot-pw/signed form) | Business Logic | 2 | 0 | 0
MVP | A. Platform Hardening & Security | Authentication & Access | Auth hardening | Token revoke + rotation endpoint | Business Logic | 2 | 1 | 0
MVP | A. Platform Hardening & Security | Authentication & Access | Auth hardening | Secure token storage (Keychain/Keystore) | Integration | 0 | 2 | 0
MVP | A. Platform Hardening & Security | Authentication & Access | Auth hardening | Session 401 handling + refresh | Business Logic | 1 | 2 | 0
MVP | A. Platform Hardening & Security | Authentication & Access | Authorization | Fine-grained RBAC (spatie roles/permissions) | Business Logic | 4 | 0 | 1
MVP | A. Platform Hardening & Security | Authentication & Access | Authorization | Policy coverage audit + gaps | Business Logic | 2 | 0 | 0
MVP | A. Platform Hardening & Security | Secrets & Config | Config hardening | Rotate + externalize Maps/Firebase keys | Integration | 1 | 1 | 0
MVP | A. Platform Hardening & Security | Secrets & Config | Config hardening | CORS configuration | CRUD/Config | 1 | 0 | 0
MVP | A. Platform Hardening & Security | Secrets & Config | Config hardening | .env.example + secrets management | Infra/DevOps | 1 | 0 | 0
MVP | A. Platform Hardening & Security | GDPR & Privacy | Account lifecycle | Account deletion (self-serve, cascade/anonymize) | Complex/Critical | 3 | 1 | 1
MVP | A. Platform Hardening & Security | GDPR & Privacy | Account lifecycle | Account deactivation / reactivation | Business Logic | 1 | 1 | 0
MVP | A. Platform Hardening & Security | GDPR & Privacy | Data rights | SAR data export (per-user) | Complex/Critical | 3 | 0 | 1
MVP | A. Platform Hardening & Security | GDPR & Privacy | Data rights | Right to erasure + retention policy jobs | Complex/Critical | 3 | 0 | 0
MVP | A. Platform Hardening & Security | GDPR & Privacy | Data rights | PII scrubbing in logs/audits | Business Logic | 2 | 0 | 0
MVP | A. Platform Hardening & Security | GDPR & Privacy | Data rights | Consent + Terms/Privacy acceptance | CRUD/Config | 1 | 1 | 0
MVP | B. Payments Integrity & Reliability | Billing correctness | Payslip & invoice | Fix payslip stub (fields + template) | Business Logic | 2 | 0 | 0
MVP | B. Payments Integrity & Reliability | Billing correctness | Payslip & invoice | Charge %/rate bounds validation | CRUD/Config | 1 | 0 | 0
MVP | B. Payments Integrity & Reliability | Billing correctness | Idempotency | Unique constraints (invoices/payslips per booking) | Data/Migration | 1 | 0 | 0
MVP | B. Payments Integrity & Reliability | Billing correctness | Idempotency | Scheduler onOneServer + withoutOverlapping | Complex/Critical | 2 | 0 | 0
MVP | B. Payments Integrity & Reliability | Billing correctness | Idempotency | Job retry/backoff/failed handling | Integration | 2 | 0 | 0
MVP | B. Payments Integrity & Reliability | Reliability & Infra | Observability | Crash reporting (Sentry + Crashlytics on) | Integration | 1 | 1 | 0
MVP | B. Payments Integrity & Reliability | Reliability & Infra | Observability | Backup + monitoring/alerts setup | Infra/DevOps | 2 | 0 | 0
MVP | B. Payments Integrity & Reliability | Reliability & Infra | Observability | Horizon retry / queue tuning | Infra/DevOps | 1 | 0 | 0
MVP | B. Payments Integrity & Reliability | Reliability & Infra | DB integrity | money -> 2-column refactor (amount_minor+currency) | Complex/Critical | 3 | 0 | 0
MVP | B. Payments Integrity & Reliability | Reliability & Infra | DB integrity | Indexes + FK + soft-delete cascade fixes | Data/Migration | 2 | 0 | 0
MVP | B. Payments Integrity & Reliability | Quality baseline | Test & CI | Test harness bootstrap (factories/fixtures) | Infra/DevOps | 2 | 1 | 0
MVP | B. Payments Integrity & Reliability | Quality baseline | Test & CI | CI/CD pipelines (2 repos) | Infra/DevOps | 2 | 1 | 0
MVP | C. Booking & Allocation | Multi-headcount booking | Booking entity | Booking model + migration (per-person) | Data/Migration | 2 | 0 | 0
MVP | C. Booking & Allocation | Multi-headcount booking | Booking entity | AdvertStatus refactor (partial-fill) | Business Logic | 3 | 0 | 0
MVP | C. Booking & Allocation | Multi-headcount booking | Booking entity | Accept -> create Booking + allocation | Business Logic | 3 | 0 | 0
MVP | C. Booking & Allocation | Multi-headcount booking | Advert management | Advert edit/update (API + admin) | CRUD/Config | 2 | 0 | 1
MVP | C. Booking & Allocation | Multi-headcount booking | Advert management | Headcount N on advert (create/list UI) | UI Standard | 1 | 2 | 1
MVP | C. Booking & Allocation | Multi-headcount booking | Booking views | Applicant booking views (per-person) | UI Standard | 0 | 3 | 0
MVP | C. Booking & Allocation | Multi-headcount booking | Booking views | Advertiser booking / coverage views | UI Standard | 0 | 2 | 2
MVP | D. Timesheet & Billing Rewire | Timesheet | Capture | Timesheet model + enum + migration | Data/Migration | 2 | 0 | 0
MVP | D. Timesheet & Billing Rewire | Timesheet | Capture | SubmitTimesheet handler + API | Business Logic | 2 | 0 | 0
MVP | D. Timesheet & Billing Rewire | Timesheet | Capture | Applicant submit timesheet UI | UI Standard | 0 | 4 | 0
MVP | D. Timesheet & Billing Rewire | Timesheet | Approval | Approve/Dispute/Query handlers | Business Logic | 3 | 0 | 0
MVP | D. Timesheet & Billing Rewire | Timesheet | Approval | Advertiser approve timesheet UI | UI Standard | 0 | 3 | 1
MVP | D. Timesheet & Billing Rewire | Billing rewire | Billing from actual hours | Rewire charge/pay to approved hours | Complex/Critical | 4 | 0 | 0
MVP | D. Timesheet & Billing Rewire | Billing rewire | Billing from actual hours | Trigger change (approved gate, not ends_at) | Business Logic | 2 | 0 | 0
MVP | D. Timesheet & Billing Rewire | Billing rewire | Billing from actual hours | Payslip real (gross/net) generation | Business Logic | 2 | 0 | 0
MVP | E. Availability & Matching | Availability | Availability model | Availability model + API | CRUD/Config | 2 | 0 | 0
MVP | E. Availability & Matching | Availability | Availability model | Availability picker UI | UI Standard | 0 | 4 | 0
MVP | E. Availability & Matching | Availability | Availability model | Double-booking guard | Business Logic | 2 | 0 | 0
MVP | E. Availability & Matching | Matching | Ranked suggestions | Ranked scoring (compliant+avail+proximity) | Complex/Critical | 4 | 0 | 0
MVP | E. Availability & Matching | Matching | Ranked suggestions | Suggested-candidates UI (advertiser) | UI Standard | 0 | 3 | 1
MVP | F. Compliance (Yedi DBS/Safeguarding) | Structured credentials | Credential model | compliance_credentials model+enum+migration | Data/Migration | 2 | 0 | 0
MVP | F. Compliance (Yedi DBS/Safeguarding) | Structured credentials | Credential model | Typed fields (DBS number/level/dates, QTS) | Business Logic | 2 | 0 | 0
MVP | F. Compliance (Yedi DBS/Safeguarding) | Structured credentials | Credential model | Expiry columns + admin entry (Filament) | CRUD/Config | 2 | 0 | 2
MVP | F. Compliance (Yedi DBS/Safeguarding) | Structured credentials | Enforcement | Auto-compute compliance status | Business Logic | 3 | 0 | 0
MVP | F. Compliance (Yedi DBS/Safeguarding) | Structured credentials | Enforcement | ExpireCredentials scheduled command | Business Logic | 1 | 0 | 0
MVP | F. Compliance (Yedi DBS/Safeguarding) | Structured credentials | Enforcement | Booking gate by expiry (AdvertPolicy) | Business Logic | 2 | 0 | 0
MVP | F. Compliance (Yedi DBS/Safeguarding) | Structured credentials | Enforcement | Compliance warnings UI (applicant) | UI Standard | 0 | 2 | 0
MVP | G. Payroll (Umbrella) | Umbrella integration | Connector | PayrollProvider connector (typed HTTP) | Integration | 4 | 0 | 0
MVP | G. Payroll (Umbrella) | Umbrella integration | Connector | Feed assignment data (hours/rate/dates) | Integration | 3 | 0 | 0
MVP | G. Payroll (Umbrella) | Umbrella integration | Connector | Payslip proxy + display | Integration | 2 | 2 | 0
MVP | G. Payroll (Umbrella) | Umbrella integration | Compliance | Worker umbrella onboarding handoff | Integration | 2 | 2 | 0
MVP | G. Payroll (Umbrella) | Umbrella integration | Compliance | AWR 12-week tracking | Business Logic | 2 | 0 | 0
MVP | H. Reporting & Brand-Policy | Reporting | Reports | Export API (CSV) | Business Logic | 2 | 0 | 1
MVP | H. Reporting & Brand-Policy | Reporting | Reports | Client dashboard (fill-rate/spend/cover) | UI Standard | 2 | 0 | 4
MVP | H. Reporting & Brand-Policy | Reporting | Reports | Admin report widgets | UI Standard | 0 | 0 | 2
MVP | H. Reporting & Brand-Policy | Brand-policy & multi-tenant | Policy layer | Brand-policy DB layer (Settings ext) | Business Logic | 3 | 0 | 0
MVP | H. Reporting & Brand-Policy | Brand-policy & multi-tenant | Policy layer | Config resolver (compliance/payroll/matching) | Business Logic | 2 | 0 | 0
MVP | I. Cross-Cutting UX & Platform | UX completeness | States & search | Search & filter (adverts/candidates) | Business Logic | 2 | 3 | 1
MVP | I. Cross-Cutting UX & Platform | UX completeness | States & search | Empty / error / loading states (all screens) | UI Standard | 0 | 4 | 1
MVP | I. Cross-Cutting UX & Platform | UX completeness | States & search | Onboarding / first-run / tutorials | UI Standard | 0 | 3 | 0
MVP | I. Cross-Cutting UX & Platform | UX completeness | States & search | Notification preferences / opt-out | CRUD/Config | 1 | 2 | 0
MVP | I. Cross-Cutting UX & Platform | UX completeness | States & search | Pagination / infinite scroll | UI Standard | 1 | 2 | 0
MVP | I. Cross-Cutting UX & Platform | UX completeness | States & search | Offline handling + connectivity | Business Logic | 0 | 3 | 0
MVP | I. Cross-Cutting UX & Platform | UX completeness | Platform | i18n / timezone handling | Business Logic | 1 | 2 | 0
MVP | I. Cross-Cutting UX & Platform | UX completeness | Platform | App force-update / version gate | Integration | 0 | 1 | 0
MVP | I. Cross-Cutting UX & Platform | UX completeness | Platform | Accessibility (a11y) pass | UI Standard | 0 | 2 | 1
MVP | I. Cross-Cutting UX & Platform | UX completeness | Platform | Analytics / event tracking | Integration | 1 | 1 | 0
Phase 2 | P2-A. Scale & Operations | Horizontal scaling | Multi-instance | Stateless app + shared session/cache | Complex/Critical | 4 | 0 | 0
Phase 2 | P2-A. Scale & Operations | Horizontal scaling | Multi-instance | Load balancer + health/readiness probes | Infra/DevOps | 2 | 0 | 0
Phase 2 | P2-A. Scale & Operations | Horizontal scaling | Multi-instance | Distributed scheduler / leader-election | Complex/Critical | 3 | 0 | 0
Phase 2 | P2-A. Scale & Operations | Horizontal scaling | Multi-instance | Multi-instance queue tuning | Infra/DevOps | 2 | 0 | 0
Phase 2 | P2-A. Scale & Operations | Ops tooling | Support | Admin impersonation / support login | Business Logic | 3 | 0 | 1
Phase 2 | P2-A. Scale & Operations | Ops tooling | Support | Maintenance mode | CRUD/Config | 1 | 1 | 1
Phase 2 | P2-A. Scale & Operations | Ops tooling | Support | Demo / seed-data environments | Infra/DevOps | 2 | 0 | 0
Phase 2 | P2-A. Scale & Operations | Ops tooling | Support | AV scanning of uploads (ClamAV integration) | Integration | 3 | 0 | 0
Phase 2 | P2-B. Revenue & Payments | Adjustments | Corrections | Refunds / adjustments / credit notes | Complex/Critical | 5 | 1 | 2
Phase 2 | P2-B. Revenue & Payments | Adjustments | Corrections | Dispute / chargeback handling | Business Logic | 3 | 0 | 1
Phase 2 | P2-B. Revenue & Payments | Payroll expansion | In-house PAYE | PAYE engine (income tax + NI calc) | Complex/Critical | 8 | 0 | 0
Phase 2 | P2-B. Revenue & Payments | Payroll expansion | In-house PAYE | RTI submission (HMRC FPS/EPS) | Integration | 5 | 0 | 0
Phase 2 | P2-B. Revenue & Payments | Payroll expansion | In-house PAYE | Pension auto-enrolment | Business Logic | 4 | 0 | 0
Phase 2 | P2-B. Revenue & Payments | Payroll expansion | In-house PAYE | Holiday pay accrual | Business Logic | 3 | 0 | 0
Phase 2 | P2-B. Revenue & Payments | Payroll expansion | Providers | Additional umbrella/payroll providers | Integration | 4 | 0 | 0
Phase 2 | P2-B. Revenue & Payments | Multi-currency | Currency | Multi-currency support | Complex/Critical | 4 | 2 | 1
Phase 2 | P2-C. Growth & Intelligence | Smart matching | Automation | Automated matching engine (scoring + auto-offer) | Complex/Critical | 6 | 2 | 0
Phase 2 | P2-C. Growth & Intelligence | Smart matching | Automation | Learning from placement outcomes | Complex/Critical | 5 | 0 | 0
Phase 2 | P2-C. Growth & Intelligence | Smart matching | Automation | Predictive staffing demand | Complex/Critical | 4 | 0 | 0
Phase 2 | P2-C. Growth & Intelligence | Analytics & BI | Dashboards | Advanced analytics / BI dashboards | Business Logic | 4 | 0 | 5
Phase 2 | P2-C. Growth & Intelligence | Analytics & BI | Dashboards | Regional performance dashboards | UI Standard | 2 | 0 | 3
Phase 2 | P2-C. Growth & Intelligence | Analytics & BI | Dashboards | Candidate performance scoring | Business Logic | 3 | 0 | 0
Phase 2 | P2-C. Growth & Intelligence | Engagement | Worker features | Ratings depth / 2-way feedback | Business Logic | 2 | 3 | 0
Phase 2 | P2-C. Growth & Intelligence | Engagement | Worker features | Referral programme | Business Logic | 3 | 3 | 0
Phase 2 | P2-C. Growth & Intelligence | Engagement | Worker features | In-app training / onboarding modules | UI Standard | 2 | 4 | 0
Phase 2 | P2-C. Growth & Intelligence | Engagement | Worker features | Worker rewards | Business Logic | 3 | 2 | 0
Phase 2 | P2-C. Growth & Intelligence | Engagement | Worker features | Calendar integration | Integration | 2 | 3 | 0
Phase 2 | P2-D. Advanced Compliance & Talent | Full DBS engine | Automation | DBS Update Service API integration | Integration | 5 | 0 | 0
Phase 2 | P2-D. Advanced Compliance & Talent | Full DBS engine | Automation | Barred-list check | Integration | 3 | 0 | 0
Phase 2 | P2-D. Advanced Compliance & Talent | Full DBS engine | Automation | Automated compliance reminders | Business Logic | 2 | 1 | 0
Phase 2 | P2-D. Advanced Compliance & Talent | Talent | Pools & self-serve | Talent pools by city/brand | Business Logic | 3 | 2 | 1
Phase 2 | P2-D. Advanced Compliance & Talent | Talent | Pools & self-serve | Client self-serve booking | Business Logic | 4 | 2 | 2
Phase 2 | P2-D. Advanced Compliance & Talent | Talent | Pools & self-serve | Additional brand onboarding (multi-tenant) | Business Logic | 4 | 0 | 1
TOTAL

## Summary
SUMMARY
MVP (delivery efficiency applied)
| Total md | Coding md | Cost
Effort & cost
+ Contingency 12%
GRAND TOTAL
PHASE 2 (delivery efficiency applied)
| Total md | Coding md | Cost
Effort & cost
+ Contingency 12%
GRAND TOTAL
MVP + PHASE 2 (combined)
Grand total md
Per-EPIC rollup | Total md | Cost
A. Platform Hardening & Security
B. Payments Integrity & Reliability
C. Booking & Allocation
D. Timesheet & Billing Rewire
E. Availability & Matching
F. Compliance (Yedi DBS/Safeguarding)
G. Payroll (Umbrella)
H. Reporting & Brand-Policy
I. Cross-Cutting UX & Platform
P2-A. Scale & Operations
P2-B. Revenue & Payments
P2-C. Growth & Intelligence
P2-D. Advanced Compliance & Talent

## Missing-Features Checklist
Category | Commonly-missed item | In WBS? | Where / Note
Account | Account deletion (self-serve) | Yes | MVP EPIC A
Account | Deactivation/reactivation | Yes | MVP EPIC A
GDPR | Data export / SAR | Yes | MVP EPIC A
GDPR | Right to erasure + retention | Yes | MVP EPIC A
GDPR | Consent + Terms/Privacy | Yes | MVP EPIC A
GDPR | PII scrubbing logs/audits | Yes | MVP EPIC A
Discovery | Search & filter | Yes | MVP EPIC I
UX | Empty/error/loading states | Yes | MVP EPIC I
UX | Onboarding / first-run | Yes | MVP EPIC I
UX | Offline handling | Yes | MVP EPIC I
UX | Pagination | Yes | MVP EPIC I
Notifications | Preferences / opt-out | Yes | MVP EPIC I
Platform | i18n / timezone | Yes | MVP EPIC I
Platform | Force-update / version gate | Yes | MVP EPIC I
Platform | Accessibility (a11y) | Yes | MVP EPIC I
Platform | Analytics / event tracking | Yes | MVP EPIC I
Security | Rate limiting | Yes | MVP EPIC A
Security | Session expiry / re-auth | Yes | MVP EPIC A
Security | AV scan of uploads | Yes (P2) | Phase 2 P2-A (was flagged out of MVP)
Ops | Audit log / activity history | Partly | owen-it exists (reuse); admin view TBC
Ops | Admin impersonation / support | Yes (P2) | Phase 2 P2-A
Ops | Maintenance mode | Yes (P2) | Phase 2 P2-A
Ops | Demo/seed data | Yes (P2) | Phase 2 P2-A
Payments | Refund / credit note | Yes (P2) | Phase 2 P2-B
Payments | Multi-currency | Yes (P2) | Phase 2 P2-B
Payroll | In-house PAYE / RTI | Yes (P2) | Phase 2 P2-B
Compliance | Full DBS Update Service | Yes (P2) | Phase 2 P2-D

## Self-Review
SELF-REVIEW CHECKLIST - before submitting
Done? | Check | Owner
[ ] | Every row has Phase (MVP/Phase 2), EPIC->Feature->Sub-Feature->Function, a Task Type and non-zero estimate.
[ ] | Delivery Efficiency factor (0.70) is a CONSCIOUS client-directed cut; risk acknowledged; sensitivity at 0.85 reviewed.
[ ] | AI reduction only via 'AI Factors'; efficiency factor applied once, globally (not double-counted).
[ ] | Effort ratio 10/10/50/30 sums to 100%; Testing only in ratio (not separate coding rows).
[ ] | MVP timeline 1.5-2 months requires a larger concurrent team - staffing confirmed feasible.
[ ] | Correctness-critical items (payments, compliance gate, PAYE, matching) still LOW AI reduction despite the cut.
[ ] | Missing-Features checklist reviewed; MVP vs Phase 2 placement agreed.
[ ] | GDPR must-haves in MVP; scale/PAYE/refunds/full-DBS in Phase 2.
[ ] | Rates sheet is single source of truth; no hard-coded costs; currency confirmed (USD vs GBP).
[ ] | Critical path respected: idempotency + timesheet before billing rewire; compliance model before gate.
[ ] | Phase 2 total is indicative (roadmap) - to be re-confirmed nearer the time.
[ ] | Grand totals reconcile with the compressed target; contingency reflects brownfield + external-dependency risk.
[ ] | Discipline split staffable (enough Flutter/Mobile capacity for the compressed schedule).